## W1-W3 Status (updated)
MarketCatalyst — W1–W3 + Milestone 1/2 Status (refreshed 2026-07-21)
ALL DEPLOYED to production (single project market-catalyst-502415). Overall avg completion 93% across 18 deliverables; 5 at 100%. Remaining gaps: deferred AI (your choice), vendor-blocked features, and heavier data backfills.
Rel / Week | Dates | Deliverable | Completion % | Pushed to Production? | Reason (if not 100%) | Suggestion to reach 100%
W1 | 06 Jul | FOUNDATION: deploy FE+BE 24/7, Blaze, service-account, indexes+TTL | 100% | ✅ Deployed — UI marketcatalyst.web.app + backend Cloud Run rev 00023 | — | Complete — retention activated (RETENTION_DRY_RUN=false, 0 eligible verified). Native TTL impossible (ISO-string dates); in-code retention enforces it. Runtime SA least-privilege.
W1 | 06 Jul | Feature-flag system (feature_flags doc, per-release FF_* toggles) | 100% | ✅ Deployed — UI marketcatalyst.web.app + backend Cloud Run rev 00023 | — | Complete — resolver + API + UI gating live; doc auto-seeded 25 flags; read rule deployed.
W1 | 06 Jul | Project setup: Firebase, Polygon subscription + API keys, verification | 100% | ✅ Yes | — | Complete.
W1 | 06 Jul | Run all sync jobs once; verify sync_meta + ops dashboard | 100% | ✅ Yes | — | Complete — now 24 jobs (added financials, market-breadth, retention).
W1 | 06 Jul | Market Movers live (gainers/losers/unusual-vol/RVol/filter) | 93% | ✅ Deployed — UI marketcatalyst.web.app + backend Cloud Run rev 00023 | Catalyst column is a news-presence heuristic, not true event attribution. MA-posture / week% / tech-context are real & live. | Correlate each mover with same-day news/earnings/analyst events for a true catalyst; else the honest heuristic stands.
W1 | 06 Jul | Market Heatmap live (sector %, tiles, summary) | 97% | ✅ Deployed — UI marketcatalyst.web.app + backend Cloud Run rev 00023 | No S&P 500 constituent list, so the dead 'S&P 500' tab was repurposed to a real Day%/Week% heat toggle. Tooltip reads live companies. | Source an S&P 500 membership list from a vendor to add a genuine index filter as a third view.
W1 | 06 Jul | Dashboard core widgets live (AI card → R34) | 92% | ✅ Deployed — UI marketcatalyst.web.app + backend Cloud Run rev 00023 | Recaps card still a .txt stub (needs R28 recap job). 'What Matters Now' AI card is a labeled placeholder (AI deferred by your decision). Internals + F&G history now live. | Build the R28 Recaps EOD job; wire Anthropic (R34) for the AI card when AI is enabled.
W2 | 13 Jul | Macro & VIX live (econ calendar + dividends + VIX/yields) | 95% | ✅ Deployed — UI marketcatalyst.web.app + backend Cloud Run rev 00023 | VIX shown via VIXY ETN proxy (plan has no spot-VIX) — labeled. Econ-calendar fallback now carries a Sample badge. | Upgrade the data plan for spot VIX if exact levels matter; otherwise the labeled proxy is fine.
W2 | 13 Jul | IPOs live (calendar + offer price) | 95% | ✅ Deployed — UI marketcatalyst.web.app + backend Cloud Run rev 00023 | Aftermarket returns now REAL for IPOs listed within the 45-day sync window (current price, day-1 close, return-since-offer via Polygon aggs). Marquee historical names still use the sample showcase. | Add a one-time backfill of notable recent IPOs (fetch aggs once) to replace the sample showcase table.
W2 | 13 Jul | Commentary/News live (aggregated feed + tags + drawer) | 82% | ✅ Deployed — UI marketcatalyst.web.app + backend Cloud Run rev 00023 | Main feed is live; Premarket/After-hours/General cards are static copy — now carry a Sample badge, but not yet live-driven. | Derive premarket/after-hours items from news publishedAt timestamps to make them live.
W2 | 13 Jul | Sector Themes live (per-stock prices + theme perf) | 82% | ✅ Deployed — UI marketcatalyst.web.app + backend Cloud Run rev 00023 | Live prices overlay per ticker; unmatched tickers show frozen sample prices — now flagged with a Sample badge. | Expand universe coverage for theme constituents so fewer rows fall back to frozen prices.
W2 | 13 Jul | Company-name search (nameLower/tokens) | 100% | ✅ Deployed — UI marketcatalyst.web.app | — | Complete — ALL search boxes now match ticker AND company name over the live universe: ⌘K palette, the Search page (was ticker-only), and the Watchlist/Portfolio add modals (new live typeahead). Options/Commentary already matched name.
W3 | 20 Jul | Portfolio Pulse live (holdings + prices + P&L + totals) | 90% | ✅ Deployed — UI marketcatalyst.web.app + backend Cloud Run rev 00023 | Real holdings + live prices + P&L work; dashboard fake $128,430 fallback removed. Pre-signin Portfolio screen still shows demo data. | Label the pre-signin demo portfolio, or gate behind an 'add your first holding' empty state.
W3 | 20 Jul | Watchlist live (persistence + prices + AI summary) | 85% | ✅ Deployed — UI marketcatalyst.web.app + backend Cloud Run rev 00023 | Persistence + live prices complete. 'AI summary' is a template (AI deferred by your decision). | Wire Anthropic (R34) for a real summary when AI is enabled; until then it's a heuristic summary.
W3 | 20 Jul | Empty-states + graceful fallback polish (cross-screen) | 92% | ✅ Deployed — UI marketcatalyst.web.app + backend Cloud Run rev 00023 | SampleBadge applied to the main silent-fallback surfaces (Recap, Themes, Macro, Commentary, Analyst, Insider). A few minor sub-cards remain unlabeled. | Apply <SampleBadge> to the last remaining fallbacks (a few dashboard sub-cards) for full coverage.
— Milestone 1 & 2 items (W4/W5), delivered early this session —
W4 | 27 Jul | Stock Detail live — financials/EPS/pivots (Milestone 1) | 80% | ✅ Deployed — UI marketcatalyst.web.app + backend Cloud Run rev 00023 | Financials, 10-quarter EPS, pivots, SMA rows all REAL. Remaining gap is data not fabrication: 1D/1W need intraday bars (not synced); 5Y needs 5yr history (only ~300d). | Add an intraday-bars sync for 1D/1W; extend the ohlcv_bars backfill to 5 years for the 5Y chart.
W4 | 27 Jul | Dashboard Fear & Greed gauge live (Milestone 2) | 95% | ✅ Deployed — UI marketcatalyst.web.app + backend Cloud Run rev 00023 | Gauge value uses the full 4-component composite; the HISTORY sparkline is a breadth-derived proxy (no long history for SPY/TLT/VIXY). | Backfill SPY/TLT/VIXY price history so F&G history uses the full composite instead of breadth alone.
W5 | 03 Aug | 10-quarter EPS history (Milestone 1) | 100% | ✅ Deployed — UI marketcatalyst.web.app + backend Cloud Run rev 00023 | — | Complete — 10 real actual quarters (Polygon /vX) + estimate line now filled from Finnhub /calendar/earnings on top of FMP.
ROLLUP |  | 18 deliverables · avg 93% · 6 at 100%

## Delivery Plan (W1-W10)
MarketCatalyst — 10-Week Delivery Plan · independently-releasable slices
Start Mon 06 Jul 2026 → finish Fri 11 Sep 2026. Each row is a self-contained RELEASE (R#) — a vertical slice (data job → wire → test) gated by its own feature flag, so it ships to production ON ITS OWN, in any order, once its 'Depends on' is met. Only R0 (Foundation) + the marked ENABLERS/keys are shared prerequisites. The fallback-to-mock pattern means flipping a release's flag lights it up without affecting any other release.
Rel. | Week | Dates | Deliverable — independently releasable | Depends on | Release gate (flag) | Dev | Test | Tot | Pri
W1 | 06 Jul |  | ▸ MILESTONE (shippable): 🚀 Platform live + first market screens — each releasable on its own
| W1 | 06 Jul–10 Jul | FOUNDATION: deploy FE+BE 24/7, Firestore→Blaze, service-account.json, indexes + TTL | — | (platform) | 2 | 1 | 3 | P0
| W1 | 06 Jul–10 Jul | Feature-flag system (env + Firestore `feature_flags` doc; every release reads its own flag → toggle independently) | R0 | (enabler) | 1 | 0.5 | 1.5 | P0
| W1 | 06 Jul–10 Jul | Project setup: Firebase, Polygon subscription + API keys, data-source verification | — | (enabler) | 1 | 0.5 | 1.5 | P0
| W1 | 06 Jul–10 Jul | Run all sync jobs once; verify sync_meta + ops dashboard | R0 | (enabler) | 1 | 1 | 2 | P0
| W1 | 06 Jul–10 Jul | Market Movers live (gainers/losers/unusual-vol/RVol/filter) | R0 + market-movers job | FF_MOVERS | 0.5 | 1 | 1.5 | P0
| W1 | 06 Jul–10 Jul | Market Heatmap live (sector %, tiles, summary) | R0 + sectors job | FF_HEATMAP | 0.5 | 0.5 | 1 | P0
| W1 | 06 Jul–10 Jul | Dashboard core widgets live (UI complete; AI card → R19) | R0 + market/movers/earnings jobs | FF_DASHBOARD | 1 | 1 | 2 | P0
W2 | 13 Jul |  | ▸ MILESTONE (shippable): Context & calendar screens + name search — 5 independent releases
| W2 | 13 Jul–17 Jul | Macro & VIX live (econ calendar + dividends + VIX/yields) | R0 + macro/dividends/indices jobs | FF_MACRO | 1 | 1 | 2 | P0
| W2 | 13 Jul–17 Jul | IPOs live (calendar + offer price) | R0 + ipos job | FF_IPOS | 0.5 | 0.5 | 1 | P0
| W2 | 13 Jul–17 Jul | Commentary/News live (multi-source aggregated feed + tags + drawer) | R0 + news job | FF_NEWS | 1 | 1 | 2 | P0
| W2 | 13 Jul–17 Jul | Sector Themes live (per-stock prices + theme perf) | R0 + companies/sectors | FF_THEMES | 1 | 0.5 | 1.5 | P1
| W2 | 13 Jul–17 Jul | Company-name search (ticker-universe re-run → nameLower/tokens) | R0 + ticker-universe rerun | FF_NAMESEARCH | 0.5 | 0.5 | 1 | P1
W3 | 20 Jul |  | ▸ MILESTONE (shippable): 'My Money' screens — 2 independent releases
| W3 | 20 Jul–24 Jul | Portfolio Pulse live (holdings + live prices + P&L + totals) | R0 + user data + companies | FF_PORTFOLIO | 1 | 1.5 | 2.5 | P0
| W3 | 20 Jul–24 Jul | Watchlist live (persistence + live prices + AI summary) | R0 + user data | FF_WATCHLIST | 1 | 1 | 2 | P0
| W3 | 20 Jul–24 Jul | Empty-states + graceful fallback polish (cross-screen) | R0 | (quality) | 1 | 1 | 2 | P1
W4 | 27 Jul |  | ▸ MILESTONE (shippable): Research screens — enabler + 3 independent releases
| W4 | 27 Jul–31 Jul | ENABLER: backfill ohlcv_bars + run compute jobs (rs-rating, technical-indicators, tech-rating, fundamentals-growth, fear-greed) | R0 | (enables R12–R14) | 1.5 | 1.5 | 3 | P0
| W4 | 27 Jul–31 Jul | Stock Detail live (charts/RSI-MACD/fundamentals/52-wk/consensus/news/insider) | R11 | FF_STOCKDETAIL | 1.5 | 2 | 3.5 | P0
| W4 | 27 Jul–31 Jul | Screener live (all filters + Tech Rating + RVOL + growth/margin) | R11 | FF_SCREENER | 1 | 1.5 | 2.5 | P0
| W4 | 27 Jul–31 Jul | Dashboard Fear & Greed gauge live | R11 (fear-greed job) | FF_FEARGREED | 0.5 | 0.5 | 1 | P1
W5 | 03 Aug |  | ▸ MILESTONE (shippable): Recaps data + data-depth — independently releasable
| W5 | 03 Aug–07 Aug | Recaps EOD data job (index returns, sector heatmap, earnings movers, internals) | R0 | FF_RECAPS_DATA | 3 | 1 | 4 | P0
| W5 | 03 Aug–07 Aug | 10-quarter EPS history (backend quarterly financials + wire) | R0 | FF_EPSHIST | 1.5 | 0.5 | 2 | P0
| W5 | 03 Aug–07 Aug | Screener sector/cap classification + IPO recent performance + Macro regime label | R0 | (extends R13/R5/R4) | 2 | 1 | 3 | P1
W6 | 10 Aug |  | ▸ MILESTONE (shippable): Options Chain — one key-gated release [Tradier / Polygon-Options]
R18 | W6 | 10 Aug–14 Aug | Options Chain live: adapter (bid/ask/IV/OI/Greeks) + full chain/expiry/Greeks wire | R0 + Options key | FF_OPTIONS | 5.5 | 2.5 | 8 | P0
W7 | 17 Aug |  | ▸ MILESTONE (shippable): AI market intel — Dashboard + Recaps feature-complete [Claude]
| W7 | 17 Aug–21 Aug | ENABLER: AI service + ANTHROPIC_API_KEY + prompt/caching infra | R0 + Claude key | (enables R19–R22) | 2 | 0.5 | 2.5 | P0
| W7 | 17 Aug–21 Aug | Dashboard 'What Matters Now' AI card → Dashboard FEATURE-COMPLETE | R19.0 + R3 | FF_AI_WMN | 1.5 | 0.5 | 2 | P0
| W7 | 17 Aug–21 Aug | Recaps AI narrative → Recaps FEATURE-COMPLETE | R19.0 + R15 | FF_AI_RECAPS | 2 | 1 | 3 | P0
W8 | 24 Aug |  | ▸ MILESTONE (shippable): Per-stock AI — independently releasable [Claude]
| W8 | 24 Aug–28 Aug | Stock Detail AI (thesis/risk/confidence + technical analysis) | R19.0 + R12 | FF_AI_STOCK | 3.5 | 1.5 | 5 | P1
| W8 | 24 Aug–28 Aug | Earnings + Analyst + Insider + Watchlist AI notes/summaries | R19.0 | FF_AI_MISC | 3.5 | 1.5 | 5 | P2
W9 | 31 Aug |  | ▸ MILESTONE (shippable): Analyst/Earnings depth + flow + alerts — 4 independent releases
| W9 | 31 Aug–04 Sep | Analyst Actions per-firm event table (upgrades/downgrades/PT) | R0 + Benzinga key | FF_ANALYST_EVENTS | 3.5 | 1 | 4.5 | P0
| W9 | 31 Aug–04 Sep | Earnings depth (guidance/reaction/real-time actuals + tag pills) → feature-complete | R0 + Benzinga key | FF_EARNINGS_DEPTH | 2.5 | 1 | 3.5 | P0
| W9 | 31 Aug–04 Sep | Options flow + dark-pool prints | R0 + UW/Polygon-paid key | FF_OPTIONS_FLOW | 2 | 0.5 | 2.5 | P2
| W9 | 31 Aug–04 Sep | Alerts engine (12 alert types + watchlist toggles) | R0 | FF_ALERTS | 2.5 | 1 | 3.5 | P1
W10 | 07 Sep |  | ▸ MILESTONE (shippable): Launch candidate
| W10 | 07 Sep–11 Sep | Editorial + dropped-feature decisions (theme list, presets, trending/gaps/weekly/my-names) | R0 | (decision) | 2 | 1 | 3 | P1
| W10 | 07 Sep–11 Sep | Earnings + Macro calendars on real date ranges (structural) | R0 | FF_REAL_CALENDARS | 2 | 1 | 3 | P0
| W10 | 07 Sep–11 Sep | Full regression + empty-states + mobile + performance | all | (gate) | 1 | 3 | 4 | P0
| W10 | 07 Sep–11 Sep | Security review + launch checklist | all | (gate) | 1 | 1 | 2 | P0
WEEK TOTALS
W1 |  | 06 Jul – 10 Jul | 12.5 person-days
W2 |  | 13 Jul – 17 Jul | 7.5 person-days
W3 |  | 20 Jul – 24 Jul | 6.5 person-days
W4 |  | 27 Jul – 31 Jul | 10.0 person-days
W5 |  | 03 Aug – 07 Aug | 9.0 person-days
W6 |  | 10 Aug – 14 Aug | 8.0 person-days
W7 |  | 17 Aug – 21 Aug | 7.5 person-days
W8 |  | 24 Aug – 28 Aug | 10.0 person-days
W9 |  | 31 Aug – 04 Sep | 14.0 person-days
W10 |  | 07 Sep – 11 Sep | 12 person-days
TOTAL |  |  | 97.0 person-days · 36 releases · 06 Jul–11 Sep 2026